## UAT Form
USER ACCEPTANCE TEST (UAT) FORM - PT CHITRA PARATAMA
Project / System Name | SUPPLY CHAIN MANAGEMENT SYSTEM - ONE CHITRA
Module / Feature | SCM MODULE
Jenis Request (New / Improvement / Enhancement / Bug Fix) | NEW
No. Development Request | BIMA/SDS/2026/1
Requestor | Bekti Widyasmoro & Ali Rahman
Department | SUPPLY CHAIN MANAGEMENT
Developer / IT PIC | M.Annas Khadafi , Aditya Jarangmula Ngindra, Fahki Rohadi
Tanggal UAT | 13 Maret 2026
Versi System | Versi 1.0.0
Environment (Dev / Staging / Production) | Production
RINGKASAN HASIL UAT
Total Test Case
Pass | 57
Fail | 0
Pending | 0

## FORM
FORM USER ACCEPTANCE TEST (UAT)
1. INFORMASI UMUM
Item |  | Keterangan
Project / System Name | : | SUPPLY CHAIN MANAGEMENT SYSTEM - ONE CHITRA | 0 | 0 | 0 | 0
Module / Feature | : | SCM MODULE | 0 | 0 | 0 | 0
Jenis Request | : | V New System ☐ Improvement ☐ Enhancement ☐ Bug Fix
No. Development Request | : | BIMA/SDS/2026/1 | 0 | 0 | 0 | 0
Requestor | : | Bekti Widyasmoro & Ali Rahman | 0 | 0 | 0 | 0
Department | : | SUPPLY CHAIN MANAGEMENT | 0 | 0 | 0 | 0
Developer / IT PIC | : | M.Annas Khadafi , Aditya Jarangmula Ngindra, Fahki Rohadi | 0 | 0 | 0 | 0
Tanggal UAT | : | 13 Maret 2026 | 0 | 0 | 0 | 0
Versi System | : | Versi 1.0.0 | 0 | 0 | 0 | 0
Environment | : | ☐ Development ☐ Staging V Production
2. TUJUAN UAT
Menentukan bahwa sistem / improvement yang dikembangkan telah sesuai dengan kebutuhan bisnis dan siap untuk digunakan secara operasional.
3. RUANG LINGKUP PENGUJIAN
RINGKASAN HASIL UAT
Total Test Case | Qty
Pass | 57
Fail | 0
Pending | 0
DETAIL HASIL UAT
Test Scenario | Test Step | Expected Result | Actual Result | Status (Pass/Fail) | Remark
Detail on Attachment |  | Modul Inventory | 7/7 | Pass
|  | Purchase Order & Good Receive | 6/6 | Pass
|  | Sales Order & Quotation | 7/7 | Pass
|  | Delivery & DO Monitoring | 7/7 | Pass
|  | Stock Opname & Movements | 6/6 | Pass
|  | Warehouse Management | 5/5 | Pass
|  | Approval Workflow | 7/7 | Pass
|  | AI Inventory Forecasting | 12/12 | Pass
4. Kesimpulan
☐ Diterima (Accepted)
☐ Diterima dengan catatan
☐ Ditolak (Revisi diperlukan)
Catatan Tambahan:
..................................................................................
5 Approval
Pihak |  | Nama | Jabatan | Tanda Tangan | Tanggal
User |  | Ali Rahman
BIMA |  | Arif Maulana Ghafar
System & Digital Solutions |  | Mochamad Annas Khadafi
IT
Finance & Business Partner Manager
(F.BIM.SDS-002/00)

## Test Scenario
No | Test Scenario | Test Step | Expected Result | Actual Result | Status (Pass/Fail) | Remark
1.1 | View Inventory List | Login → Inventory → View list | Inventory table displayed correctly | Sesuai expected result | PASS | -
1.2 | Filter Inventory by Category | Open Inventory → Select category → Apply | Filtered data displayed | Sesuai expected result | PASS | -
1.3 | Search Product | Input keyword → Enter | Matching products displayed | Sesuai expected result | PASS | -
1.4 | Export Inventory to Excel | Click Export → Excel → Download | Excel downloaded successfully | Sesuai expected result | PASS | -
1.5 | Stock Comparison View | Open comparison → Select period | Stock comparison displayed | Sesuai expected result | PASS | -
1.6 | Low Stock Alert | Open alerts → Filter reorder point | Low stock items displayed | Sesuai expected result | PASS | -
1.7 | Stock Level Update | Select product → Update qty → Save | Stock updated successfully | Sesuai expected result | PASS | -
2.1 | Create Purchase Order | PO → Create → Supplier → Items → Submit | PO created with Pending status | Sesuai expected result | PASS | -
2.2 | Edit PO Draft | Select draft PO → Edit → Save | PO updated | Sesuai expected result | PASS | -
2.3 | Create Good Receive | Select PO → Create GR → Input qty | GR created and stock increased | Sesuai expected result | PASS | -
2.4 | Partial GR | Create GR with partial qty | PO status Partially Received | Sesuai expected result | PASS | -
2.5 | Complete GR | Create GR remaining qty | PO status Fully Received | Sesuai expected result | PASS | -
2.6 | Manual GR | GR Manual → Input data | Stock updated | Sesuai expected result | PASS | -
3.1 | Create Quotation | Quotation → Create → Customer → Items | Quotation created | Sesuai expected result | PASS | -
3.2 | Edit Quotation | Select quotation → Edit → Save | Quotation updated | Sesuai expected result | PASS | -
3.3 | Create SO Direct | SO → Create → Submit | SO Pending | Sesuai expected result | PASS | -
3.4 | SO Stock Validation | Create SO > stock | System shows warning | Sesuai expected result | PASS | -
3.5 | Approve SO | Select SO → Approve | SO Approved | Sesuai expected result | PASS | -
3.6 | Edit SO | Edit qty → Save | SO updated | Sesuai expected result | PASS | -
3.7 | Print SO | SO → Print | SO PDF generated | Sesuai expected result | PASS | -
4.1 | Create DO | SO Approved → Create DO | DO created and stock reduced | Sesuai expected result | PASS | -
4.2 | Partial Delivery | Create DO partial | SO Partially Delivered | Sesuai expected result | PASS | -
4.3 | Complete Delivery | Create DO remaining | SO Fully Delivered | Sesuai expected result | PASS | -
4.4 | View DO Monitoring | Open DO Monitoring | All DO displayed | Sesuai expected result | PASS | -
4.5 | Update DO Status | Change status | Status updated | Sesuai expected result | PASS | -
4.6 | Edit DO Info | Edit driver/vehicle | Information updated | Sesuai expected result | PASS | -
4.7 | Print Delivery Note | Print DO | PDF generated | Sesuai expected result | PASS | -
4.8 | Delivery Cost Request | Create request | Request submitted | Sesuai expected result | PASS | -
5.1 | Create Stock Opname | Stock Opname → Create | SO Draft created | Sesuai expected result | PASS | -
5.2 | Input Physical Count | Input physical qty | Data saved | Sesuai expected result | PASS | -
5.3 | Calculate Variance | Click calculate | Variance shown | Sesuai expected result | PASS | -
5.4 | Print Checklist | Print checklist | Checklist PDF generated | Sesuai expected result | PASS | -
5.5 | View Stock Movements | Open movements | Movement history displayed | Sesuai expected result | PASS | -
5.6 | Stock Transfer | Create transfer | Transfer request created | Sesuai expected result | PASS | -
6.1 | View Warehouse List | Open warehouse page | Warehouse list displayed | Sesuai expected result | PASS | -
6.2 | Create Warehouse | Add warehouse | Warehouse added | Sesuai expected result | PASS | -
6.3 | Edit Warehouse | Edit data | Warehouse updated | Sesuai expected result | PASS | -
6.4 | View Stoc by Warehouse | Open warehouse stock | Stock displayed | Sesuai expected result | PASS | -
6.5 | View Valuation | valuation stock | Warning displayed | Sesuai expected result | PASS | -
7.1 | View Approval Queue | Open approvals | Requests displayed | Sesuai expected result | PASS | -
7.2 | Approve Request | Approve request | Status updated | Sesuai expected result | PASS | -
7.3 | Reject Request | Reject with reason | Request rejected | Sesuai expected result | PASS | -
7.4 | Multi-level Approval | Submit multi approval | Flow works | Sesuai expected result | PASS | -
7.5 | Approval Matrix | Edit rules | Rules saved | Sesuai expected result | PASS | -
7.6 | Approval Notification | Submit request | Email sent | Sesuai expected result | PASS | -
7.7 | Export Approval Report | Export history | Report downloaded | Sesuai expected result | PASS | -
8.2 | AI Model Accuracy | 1. View prediction accuracy2. Compare with actual | Menampilkan accuracy metrics (MAPE, RMSE) | Accuracy calculation bekerja dengan benar, NaN handling fixed | PASS | Property-based tests passed
8.3 | Forecast Comparison | 1. Buka comparison view2. Pilih periode | Menampilkan grafik forecast vs actual | Comparison data aggregation berfungsi dengan baik | PASS | 8/8 comparison tests passed
8.4 | Reorder Recommendation | 1. View AI recommendations2. Check suggested qty | System memberikan rekomendasi qty order berdasarkan forecast | Rekomendasi berdasarkan historical data dan AI prediction | PASS | Logic verified
8.5 | Export AI Report | 1. Klik Export2. Download | File Excel dengan forecast data berhasil didownload | Export functionality bekerja dengan baik | PASS | Export tests passed
8.6 | AI Model Retrain | 1. Trigger model retrain2. Wait for completion | Model berhasil retrain dengan data terbaru | Cache management berfungsi, data diupdate setiap 24 jam | PASS | Cache tests passed
8.7 | Bulk Prediction Processing | 1. Upload multiple products2. Process batch3. View results | Batch processing berhasil dengan summary report | Bulk prediction: 9/9 tests passed, max 50 products, 2s delay | PASS | All bulk tests passed
8.8 | Filter by Date Range | 1. Set date filter2. Apply | Data terfilter sesuai tanggal | Filter logic diperbaiki, bekerja dengan benar | PASS | Implementation verified
8.9 | Filter by Stock Range | 1. Pilih stock range (low/medium/high)2. Apply | Data terfilter sesuai range | Medium range filter fixed, semua range bekerja | PASS | Logic fixed and verified
8.1 | Filter by Accuracy Level | 1. Pilih accuracy level2. Apply | Data terfilter sesuai accuracy | Filter conditions bekerja dengan benar | PASS | Implementation verified
8.11 | Search Products | 1. Input search query2. Search | Menampilkan produk yang match | Search by product code dan name berfungsi | PASS | Logic verified
8.12 | Pagination | 1. Navigate pages2. Change page size | Pagination berfungsi dengan smooth | Pagination dengan infinite scroll support | PASS | Pagination tests passed

## Issue Log
No | Deskripsi Issue | Severity (Low/Medium/High) | PIC | Target Fix Date | Status